# Client Project Proposal & Sprint 1 Plan

TEMPLATE & INSTRUCTIONS

# Instructions

This week (either Week 3 or 4), meet with your client and complete Part A — Project Proposal Summary — together with them. This is not a document you write about your client; it's a document you agree with your client. It becomes the shared reference point for what you're building.

Once Part A is agreed and signed off, complete Part B — your Sprint 1 Plan — allocating every task for the first 3 weeks of the Design & Bootstrap sprint across your team. Submit both parts as one document.

Roles on a real client team don't have to match the 5-role structure used in the in-class simulation. Combine or split roles based on what this specific project actually needs (e.g. a BA doubling as a developer, or two people on UX if the project is design-heavy). The only non-negotiable: it must be unambiguous who owns each task – PM,BA and UX tasks are not split, only one person in charge, but a BA can double up as UX.

# Understanding the 3-Sprint Structure

Every capstone project runs the same fixed arc, regardless of what you're building. You'll need to understand this before you can write the roadmap section in Part A. Things may change but overall your definition is always Initiation and Design > Core MVP Feature > Refine MVP  , for short we refer to this as ICR (Initiation, Core , Refined)

If the ICR does not fit your project, you still need to build your project around the three sprints, if this does not fit the client, please invite either Alessio or Nhi into the discussion.

### Sprint 1 — Design & Bootstrap

Two separate tracks run in parallel, not one. Infrastructure is real, not mocked — your web server, database, and storage are actually stood up and live by the end of this sprint. Product is NOT working code — designs and a paper prototype only (a digital mockup, e.g. Figma, is fine — it doesn't need to be literal paper). No working features yet, mocked or otherwise.

This sprint answers: is the plumbing live, and do we know what we're building? Not: does anything work yet.

### Sprint 2 — Core MVP

The single main feature that proves your project's core value proposition, built end-to-end even if rough. Not polished, not complete — but a real user or client can see the idea works. This sprint answers: does the core idea actually function?

### Sprint 3 — Refine MVP

Hardening, polish, and secondary features if time allows, fixing what Sprint 2 exposed. This sprint answers: is this now presentable and closer to production-credible?

# Part A — Project Proposal Summary

## Project Details

Project name: Telstra Health – UX Research Companion

Client / organization: Shin Lee – Telstra Health

Prepared by: Group 23 – Team 1

Date of client discussion: Initial proxy discussion on 7 August 2026

## Team & Roles

List everyone on the team and what they own. Combine roles where the project calls for it — just make sure every task in Part B maps to a name here.

| Role | Assigned to | Notes |
| --- | --- | --- |
| Project Manager | Ngoc Chau Vu | Owns sprint planning, task coordination, scope/risk tracking, supervisor communication, progress reviews, showcase preparation and final sprint sign-off. |
| Business Analyst | Shehryar Shaukat | Owns UX research synthesis, problem/workflow definition, functional requirements, user stories, acceptance criteria and design validation. |
| UX Expert | Andi Jagila | Owns UX discovery, current-state workflow mapping, user flows, wireframes, Figma prototype, design refinement and UX handoff. |
| Developer 1 | Manh Tuan Lam | Owns frontend infrastructure, application structure, deployment, live application shell and frontend–backend integration handoff. |
| Developer 2 | Rishi Sood | Owns backend infrastructure, database/storage, AI/API feasibility and architecture, security/privacy considerations and infrastructure verification. |

## Problem Statement

UX designers at Telstra Health regularly conduct research to inform product and design decisions. Yet using generative AI for these tasks can be ad hoc dependent on manually and repeatedly supplying context, which may lead to inconsistent or overly broad outputs. The project will explore how AI can support a more structured and repeatable UX research workflow for the designers.

## Target Users

Primary target user: Shin Lee – a senior UX designer at Telstra Health who regularly conducts research, gather feedback, reviews industry standards, and validates design decisions for health product development.

The solution may also be applicable to other UX designers at Telstra Health working on digital health products who perform similar research activities.

## Proposed Solution

An AI-assisted guides users through defined research processes by using stored project contexts and constraints, avoiding the need to explain the same background repeatedly. Follow-up questions will be asked to clarify the research needs and support deeper investigation, combined with collecting evidence from relevant sources and generating UX-focused outputs. The specific workflow developed as the core MVP will be refined through further research and customer validation.

## Scope Boundaries

In scope this term: Develop an active AI-powered UX Research Companion to support a structured UX research process. The tool will allow users to provide a research topic, reuse basic project context, answer follow-up questions for clarification, use existing AI services to support research, and organise results into simple UX-focused outputs.

Out of scope this term: Develop new AI models from scratch, automating the entire UX design and research process, using real patient or health information, and deeply integrating the tool with Telstra Health's internal production systems. The project will instead take an existing AI model and build on top of it to better support the needs of UX designers. Its purpose is to support UX designers rather than replace their work and avoid using sensitive health information or requiring additional access to Telstra Health's internal systems, reducing privacy, security, access and resource requirements.

## 3-Sprint Roadmap

Sprint 1 — Design & Bootstrap: Define and validate the problem and selected UX research workflow, then complete the prototype while setting up the required technical infrastructure.

Sprint 2 — Raw MVP: Build one selected AI-assisted UX research workflow end-to-end, from research clarification and context reuse to structured UX-focused results.

Sprint 3 — Refine MVP: Test and refine the core workflow based on feedback, improve usability and reliability, and polish the product for final demonstration.

## Success Criteria

- The selected UX research workflow can be completed end-to-end through the working application.

- The tool can reuse stored project context to reduce repeated background input from the user.

- The tool provides relevant follow-up questions and produces clear, structured UX-focused research outputs.

- The solution is understandable and usable for the target UX designer and is refined based on client or user feedback.

- The application is stable enough for demonstration and operates using only approved, non-sensitive information

## Assumptions & Constraints

- Direct client feedback and confirmation are still pending, so the current project direction is based on the proxy discussion, available project information and team research.

- The selected UX research workflow and requirements may be refined after direct client validation.

- The project will rely on an existing AI service or API, with the final provider and available access still to be confirmed.

- No real patient or sensitive health information will be used.

- The project must be completed within the semester timeframe and available student-level resources.

## Client Agreement

Client name: Shin Lee

Client signature / date: [Signature / Date]

Team representative: Ngoc Chau Vu

Team signature / date:

Ngoc Chau Vu

13 August 2026

## Appendix – Client Contact Attempt

Our team has not received any direct contact details for the client from the teaching team, and we have not received any email or message from the client to date.

We attempted to identify an alternative way to contact the client independently. The only relevant public information we were able to locate was the client’s LinkedIn profile; however, no direct contact details such as an email address or phone number were publicly available there. The Project Manager also contacted the PM of the other team assigned to the same project to check whether they had received any additional client contact information. They were in the same situation and were also unsure how to contact the client directly.

The issue was raised with the teaching team during the lecture. In the absence of direct client contact, we followed the guidance provided to continue progressing the project by making reasonable assumptions based on the available project brief, the proxy discussion, our own research, and supervisor feedback. Any assumptions or unconfirmed requirements have been documented and will be revisited once direct client feedback becomes available.

# Part B — Sprint 1 Plan (Weeks 1–3)

Allocate every task for the Design & Bootstrap sprint across your team, week by week. Every task must sit on either the infrastructure track or the Design/Product track — Sprint 1 has no working features on either track. The tracks are here only to help you separate things with more granularity. 
Remember that every team member needs to contribute 4 solid hours of work per week.

Two example tasks are included below (one per track) to show the level of detail expected. Replace and add cards until every piece of Sprint 1 work is on the board with a clear owner.

## Week 1

### Project Setup – Establish Sprint 1 Planner

| Owner | Ngoc Chau Vu – PM | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 1 |

Description: Set up the Sprint 1 project board and working process to ensure all Design/Product and Infrastructure work can be tracked consistently. Define task ownership, internal deadlines, and expectations.

Deliverable: Sprint 1 Planner board and agreed team working process.

Acceptance criteria:

✓ Sprint 1 tasks are created in Planner.

✓ Every task has one clear owner.

✓ Every task is assigned to Design/Product or Infrastructure.

✓ Estimated effort is recorded.

✓ Internal deadlines are recorded.

✓ Each task includes checklist items.

### User Research – Research UX Research Activities and Problems

| Owner | Shehryar Shaukat – BA | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 3.5 |

Description: Research common UX research activities and recurring problems, then use the findings to identify several candidate problem statements or research workflows that the project could focus on.

Deliverable: UX research findings and candidate problem/workflow shortlist.

Acceptance criteria:

✓ Main UX research activities are identified.

✓ Typical inputs and outputs are documented.

✓ Recurring/manual pain points are identified.

✓ Competitor/market research is considered.

✓ Multiple candidate problems/workflows are proposed.

✓ Each candidate links to an identified user pain point.

✓ Candidates remain within Part A scope.

✓ Assumptions are clearly marked.

✓ Findings are shared with UX and PM.

### UX Discovery – Map Current UX Research Journey and Pain Points

| Owner | Andi Jagila – UX | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 3.5 |

Description: Use Part A, BA research and available project information to map the current UX research journey and pain points, then evaluate which problem areas appear to offer the strongest opportunity for structured AI support.

Deliverable: Current-state workflow/journey map and UX opportunity assessment.

Acceptance criteria:

✓ Main research stages and user actions are shown.

✓ Key pain points are identified.

✓ Repeated context/prompting issues are considered.

✓ Manual or inefficient research steps are highlighted.

✓ Candidate problems are reviewed from a UX perspective.

✓ Stronger opportunity areas are identified.

✓ Assumptions are clearly marked.

✓ Findings are shared with BA and PM.

✓ No product wireframes or mockup screens are created yet.

### Frontend Infrastructure – Review & Prepare Frontend/Deployment Baseline

| Owner | Manh Tuan Lam – Dev 1 | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 1 | Hours | 3.5 |

Description: Review the existing repository and frontend setup, identify what can be reused, and prepare the frontend/deployment foundation for later Sprint 2 development.

Deliverable: Working frontend/deployment baseline.

Acceptance criteria:

✓ Existing frontend setup is reviewed.

✓ Reusable project components/setup are identified.

✓ Required project changes are identified.

✓ Frontend environment runs successfully.

✓ Base project structure is ready.

✓ Deployment approach/setup is prepared or validated.

✓ Setup/configuration is documented.

✓ No working UX Research Companion feature is implemented.

### Backend Infrastructure – Assess & Prepare AI/Backend/Storage Foundation

| Owner | Rishi Sood – Dev 2 | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 1 | Hours | 3.5 |

Description: Assess feasible AI/API options and prepare the initial backend, database and storage foundation needed for context reuse and future research workflows.

Deliverable: AI/backend/storage feasibility note and initial infrastructure baseline.

Acceptance criteria:

✓ Feasible existing AI/API approach(es) are identified.

✓ Backend requirements are identified.

✓ Database/storage needs are identified.

✓ Initial backend/database/storage environment is prepared.

✓ Basic connectivity is verified where applicable.

✓ Security/privacy considerations are documented.

✓ Sensitive health information is excluded.

✓ No working AI research feature is implemented.

### Supervisor Preparation – Prepare Week 1 Progress & Questions

| Owner | Ngoc Chau Vu – PM | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 1 |

Description: Review current progress and prepare the main updates, blockers and questions to raise with Jolly.

Deliverable: Short supervisor check-in agenda/progress summary.

Acceptance criteria:

✓ Current progress is reviewed.

✓ Main blockers/questions are prepared.

✓ Planner is ready to present.

### Supervisor Check-in – Sprint 1 Week 1 Review

| Owner | All team members | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 0.5 |

Description: Attend Jolly’s SCRUM-style Week 1 check-in to review the Planner, progress and current blockers.

Deliverable: Supervisor feedback and follow-up actions.

Acceptance criteria:

✓ Team attends.

✓ Planner/progress is reviewed.

✓ Important questions or blockers are raised.

✓ Feedback/actions are recorded.

### Week 1 Review – Update Direction & Prepare Week 2

| Owner | Ngoc Chau Vu – PM | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 1.5 |

Description: Review team outputs and Jolly’s feedback, update the Planner and confirm what should move forward into Week 2.

Deliverable: Updated Week 2 direction and action list.

Acceptance criteria:

✓ Key outputs are reviewed.

✓ Jolly’s feedback is incorporated.

✓ Week 2 priorities are confirmed.

## Week 2

### Product Direction – Select Core MVP Research Workflow

| Owner | Ngoc Chau Vu – PM | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 0.5 |

Description: Review the Week 1 research, UX findings and technical feasibility with the team and confirm the single UX research workflow that will be taken forward for Sprint 1 design and Sprint 2 implementation.

Deliverable: Confirmed Core MVP workflow and short decision note.

Acceptance criteria:

✓ Week 1 candidate workflows are reviewed.

✓ User value and technical feasibility are considered.

✓ One Core MVP workflow is selected.

✓ The selected workflow remains within Part A scope.

✓ Any remaining client-validation assumptions are recorded.

### Requirements – Define Core MVP Functional Requirements & Required Screens/States

| Owner | Shehryar Shaukat – BA | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 1.5 |

Description: Translate the selected Core MVP workflow into clear functional requirements so UX knows exactly what the future solution must support before creating wireframes. The BA defines what information and functionality must exist, not the visual layout.

Deliverable: Core MVP functional requirements and required screen/state specification.

Acceptance criteria:

✓ Main workflow stages are documented.

✓ Required user inputs are defined.

✓ Required system outputs are defined.

✓ Required screens/states are identified.

✓ Rules and scope boundaries are documented.

✓ Optional/unconfirmed functionality is clearly separated from confirmed Core MVP requirements.

### Requirements – Define User Stories, Rules & Acceptance Criteria

| Owner | Shehryar Shaukat – BA | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 1.5 |

Description: Convert the functional requirements into prioritised user stories, behavioural rules and acceptance criteria that can later guide UX validation and Sprint 2 development/testing.

Deliverable: Core MVP user story and acceptance-criteria document.

Acceptance criteria:

✓ Core user stories are documented.

✓ Each core story has testable acceptance criteria.

✓ Required versus optional behaviour is clearly separated.

✓ Important rules and edge cases are documented.

✓ Out-of-scope functionality is explicitly identified.

✓ Open questions/assumptions are recorded.

### UX Design – Create Core User Flow & Low-Fidelity Wireframes

| Owner | Andi Jagila – UX | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2 |

Description: Use the approved BA requirements to design the future-state user flow and low-fidelity wireframes for the selected Core MVP workflow. The UX designer determines how the user experiences the required functionality.

Deliverable: Core user flow and low-fidelity Figma wireframes.

Acceptance criteria:

✓ User flow covers the Core MVP from start to result.

✓ Every required screen/state from the BA specification is represented.

✓ Required inputs and actions are represented.

✓ Context reuse is represented.

✓ Clarification interaction is represented.

✓ Structured research results are represented.

✓ Relevant loading/error/empty states are considered where required.

✓ No unsupported feature is added.

### Design Validation – Validate Wireframes Against Requirements

| Owner | Shehryar Shaukat – BA | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 1 |

Description: Review the UX wireframes against the approved functional requirements, user stories and scope before the prototype is finalised.

Deliverable: Design-validation record with approved items and identified gaps.

Acceptance criteria:

✓ Each core requirement is checked against the design.

✓ Required screens/states and fields are represented.

✓ User stories can be completed through the proposed flow.

✓ No unapproved functionality has been introduced.

✓ Missing or conflicting elements are documented.

✓ Required corrections are returned to UX.

### UX Design – Resolve Gaps & Create Clickable Figma Prototype

| Owner | Andi Jagila – UX | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2 |

Description: Resolve the gaps identified during BA validation and turn the approved wireframes into a clear clickable prototype representing the Core MVP experience.

Deliverable: Validated clickable Figma prototype.

Acceptance criteria:

✓ BA validation issues are resolved.

✓ Main workflow is clickable end-to-end.

✓ Required interactions/states are represented.

✓ Screens and frames are clearly named.

✓ Main transitions are understandable.

✓ Prototype remains within approved scope.

✓ Prototype is ready for Week 3 refinement/showcase.

### Frontend Infrastructure – Define Frontend Structure & Prepare Live Application Shell

| Owner | Manh Tuan Lam – Dev 1 | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2.5 |

Description: Depends on core requirements and emerging UX flow. It does not need to wait for every pixel of the final prototype. Align the existing frontend foundation with the selected Core MVP by defining the future route/component structure and preparing the live application shell that Sprint 2 development will use.

Deliverable: Live frontend application shell and frontend structure documentation.

Acceptance criteria:

✓ Required future routes/pages/components are identified from the approved product flow.

✓ Base frontend structure is prepared.

✓ Application shell runs successfully.

✓ Live deployed URL is accessible.

✓ Environment/configuration is documented.

✓ No working Core MVP feature is implemented.

### Backend Infrastructure – Define Data Model, Backend & AI Integration Architecture

| Owner | Rishi Sood – Dev 2 | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 2 | Hours | 4 |

Description: Translate the selected workflow and approved requirements into the backend, data and AI-integration architecture required for Sprint 2.

Deliverable: Backend/data architecture, AI integration approach and prepared infrastructure foundation.

Acceptance criteria:

✓ Required backend responsibilities are defined.

✓ Data model supports the required project context and research workflow.

✓ Database/storage structure is defined and prepared.

✓ Planned frontend/backend data flow is documented.

✓ Existing AI/API integration approach is documented.

✓ Context reuse and clarification data flow are considered.

✓ API-key/secret handling is defined.

✓ Privacy constraints are respected.

✓ Only non-sensitive test/placeholder data is used.

✓ No working AI research feature is implemented.

### Infrastructure Integration – Align Frontend and Backend Technical Contract

| Owner | Manh Tuan Lam – Dev 1 | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 2 | Hours | 1.5 |

Description: Align the frontend and backend technical expectations so both developers enter Sprint 2 with a shared understanding of the data the interface will send and receive.

Deliverable: Frontend–backend integration contract / technical handoff note.

Acceptance criteria:

✓ Main frontend requests are identified.

✓ Expected backend responses are identified.

✓ Required data fields are agreed.

✓ Context/clarification/result data flow is documented.

✓ Basic error-response expectations are agreed.

✓ Dev 1 and Dev 2 confirm the technical handoff is clear.

✓ No end-to-end Core MVP functionality is implemented.

### Week 2 Review – Review Design, Infrastructure & Week 3 Readiness

| Owner | Ngoc Chau Vu – PM | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 3.5 |

Description: Continuously review progress across Week 2, coordinate handoffs between BA, UX and developers, monitor scope and blockers, review key deliverables, keep the Planner accurate and prepare the team for Week 3 finalisation/showcase work.

Deliverable: Updated Planner, documented feedback/blockers and confirmed Week 3 readiness/actions.

Acceptance criteria:

✓ BA → UX → BA handoffs are checked.

✓ Product/design progress is reviewed.

✓ Infrastructure progress is reviewed.

✓ Scope changes/blockers are recorded and followed up.

✓ Planner remains aligned with actual progress.

✓ Remaining Week 3 work is identified and assigned.

## Week 3

### UX Design – Refine Final Core MVP Prototype

| Owner | Andi Jagila – UX | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2.5 |

Description: Refine the Week 2 clickable prototype using the approved requirements, Week 2 validation feedback and any relevant team/supervisor feedback so that the complete Core MVP experience is ready for final review and showcase.

Deliverable: Refined final Figma prototype.

Acceptance criteria:

✓ Main Core MVP flow is complete end-to-end.

✓ All required screens/states are represented.

✓ Research input and reusable project context are clear.

✓ Clarification interaction is clear.

✓ Structured UX research results are clearly represented.

✓ Relevant loading/error/empty states are included where required.

✓ Week 2 feedback has been addressed.

✓ Screens, components and prototype links are clearly organised.

✓ No unapproved/out-of-scope features are introduced.

### Design Validation – Complete Final Requirements-to-Prototype Validation

| Owner | Shehryar Shaukat – BA | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2 |

Description: Perform the final formal review of the refined Figma prototype against the approved Core MVP functional requirements, user stories, rules and acceptance criteria.

Deliverable: Final design validation record.

Acceptance criteria:

✓ Every Core MVP requirement is checked against the prototype.

✓ Required inputs, screens and states are represented.

✓ Core user stories can be completed through the prototype.

✓ Required business rules are represented.

✓ No unsupported functionality has been added.

✓ Remaining assumptions are clearly documented.

✓ Any final design gaps are returned to UX.

✓ Prototype is approved for Sprint 2 development once gaps are resolved.

### UX Handoff – Resolve Final Gaps & Prepare Development/Showcase Handoff

| Owner | Andi Jagila – UX | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 1 |

Description: Resolve any final issues identified by BA and prepare the approved Figma prototype so developers can clearly understand what they need to implement in Sprint 2 and the team can confidently demonstrate the experience during the showcase.

Deliverable: Final approved Figma prototype and UX handoff.

Acceptance criteria:

✓ Final BA gaps are resolved.

✓ Main interactions are documented.

✓ Required screens/states are clearly named.

✓ Relevant design notes are included for developers.

✓ Prototype walkthrough is ready for showcase.

✓ Devs can identify the Sprint 2 flow they will implement.

### Requirements – Finalise Sprint 2 Requirements, Acceptance & Test Scenarios

| Owner | Shehryar Shaukat – BA | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 1.5 |

Description: Convert the validated Sprint 1 design into the final requirements, acceptance criteria and test scenarios that will guide Core MVP development in Sprint 2.

Deliverable: Sprint 2 Core MVP requirements and acceptance/test pack.

Acceptance criteria:

✓ Final Core MVP scope is clearly documented.

✓ User stories and acceptance criteria are finalised.

✓ Happy-path scenario is documented.

✓ Main error/edge scenarios are documented.

✓ Context reuse and clarification behaviours are covered.

✓ Structured-result expectations are covered.

✓ Optional/out-of-scope functions are clearly separated.

✓ Remaining client-validation assumptions are recorded.

✓ Requirements are ready for Dev 1 implementation and Dev 2 testing in Sprint 2.

### Frontend Infrastructure – Finalise Live Application Shell & Deployment

| Owner | Manh Tuan Lam – Dev 1 | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2.5 |

Description: Finalise the live frontend infrastructure and application shell that will be used to implement the Core MVP during Sprint 2.

Deliverable: Sprint 2-ready live frontend environment.

Acceptance criteria:

✓ Application shell builds and runs successfully.

✓ Live deployed URL is accessible.

✓ Required base routes/page structure are prepared.

✓ Frontend structure aligns with the approved workflow.

✓ Environment/configuration is documented.

✓ Deployment process is repeatable.

✓ No secrets are exposed.

✓ No working Core MVP feature is implemented.

### Backend Infrastructure – Finalise Backend, Database, Storage & AI Integration Design

| Owner | Rishi Sood – Dev 2 | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2.5 |

Description: Finalise the backend/database/storage foundation and technical AI-integration approach required to implement the validated Core MVP during Sprint 2.

Deliverable: Sprint 2-ready backend/data infrastructure and AI integration design.

Acceptance criteria:

✓ Backend/service environment is prepared.

✓ Database and required storage are operational.

✓ Core data structure supports the approved workflow.

✓ Project-context storage approach is defined.

✓ Research/clarification/result data requirements are covered.

✓ AI/API request-response approach is documented.

✓ API key/secret handling is defined.

✓ Only approved non-sensitive test data is used.

✓ No working AI research feature is implemented.

### Technical Handoff – Finalise Frontend–Backend Integration Contract

| Owner | Manh Tuan Lam – Dev 1 | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 3 | Hours | 1 |

Description: Finalise the technical contract between frontend and backend so both developers have a shared understanding of how the approved Sprint 2 workflow will be implemented.

Deliverable: Final frontend–backend technical handoff.

Acceptance criteria:

✓ Required frontend requests are documented.

✓ Expected backend responses are documented.

✓ Required data fields/formats are agreed.

✓ Context and clarification data flows are agreed.

✓ Result data expectations are agreed.

✓ Error-response expectations are documented.

✓ Dev 1 and Dev 2 confirm the handoff is clear.

✓ No Core MVP feature is implemented yet.

### Infrastructure Readiness – Verify Backend, Database & Storage Foundation

| Owner | Rishi Sood – Dev 2 | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 3 | Hours | 1 |

Description: Verify that the backend, database and storage foundations required for Sprint 2 are operational and match the final technical handoff.

Deliverable: Infrastructure readiness record.

Acceptance criteria:

✓ Backend/service is reachable.

✓ Database/storage connectivity is confirmed.

✓ Required configuration is present.

✓ Non-sensitive placeholder/test operations work where applicable.

✓ Technical setup matches the agreed integration contract.

✓ Known limitations/blockers are documented.

✓ Infrastructure is ready for Sprint 2 development.

### Sprint Review – Coordinate Final Sprint 1 Review & Showcase Preparation

| Owner | Ngoc Chau Vu – PM | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 3.5 |

Description: Track Week 3 progress across BA, UX and Infrastructure, coordinate final handoffs, review Sprint 1 deliverables against Part A, resolve outstanding blockers and prepare the team’s Week 3 showcase with Jolly.

Deliverable: Showcase-ready Sprint 1 package, updated Planner and Sprint 2 readiness summary.

Acceptance criteria:

✓ Required Sprint 1 deliverables are reviewed.

✓ Final prototype and BA validation are complete.

✓ Infrastructure readiness is checked.

✓ Remaining risks/assumptions are recorded.

✓ Showcase flow and team speaking roles are prepared.

✓ Planner accurately reflects Sprint 1 status.

✓ Sprint 2 next steps are clear.

### Showcase – Present Sprint 1 Outcomes to Supervisor

| Owner | All team members | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 0.5 |

Description: Present the Sprint 1 outcomes to Jolly during the marked Week 3 showcase, demonstrating that the team understands the problem, knows what it will build and has the technical plumbing ready for Sprint 2.

Deliverable: Completed Sprint 1 showcase and captured supervisor feedback.

Acceptance criteria:

✓ All team members attend.

✓ Problem and selected workflow are clearly explained.

✓ Research/requirements rationale is presented.

✓ Final Figma prototype is demonstrated.

✓ Live technical infrastructure status is shown/explained.

✓ Team clearly distinguishes completed Sprint 1 work from Sprint 2 functionality.

✓ Remaining assumptions/limitations are acknowledged.

✓ Sprint 2 plan is explained.

✓ Supervisor feedback and follow-up actions are recorded.