## Plan
Plan ID | Plan name | Date of export
oX5eDlBL4UKyl3dOH7jMucgAEudp | Week 4 - project : Team 23 | 2026-08-14

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
kMlAPPkaf0mSF-V2f1QjHMgAOziU | Labels | Documents & Updates |  | Not started | Medium |  | Ngoc Chau Vu | 2026-08-07 |  |  |  | false
QbxsMkKnRkWu6R4_im8vWcgAG7N9 | [BOOTSTRAP RESTYLING] -Write requirements for team page + login styling : 60 | Done |  | Completed | Important | Shehryar Shaukat | Ngoc Chau Vu | 2026-08-07 | 2026-08-10 | 2026-08-10 |  | false | 2026-08-11 | Ngoc Chau Vu | 5/5 | Team page fields listed with validation/display rules;Edge cases documented;Login scope explicitly stated as styling-only;Document updated;Requirements shared with PM and UX | BA;Sprint 1 | Description Determine the content fields for the team page (name, photo, role, blurb) and confirm the login work is styling only, with no changes to existing auth logic or session behavior. Document edge cases such as missing photos or long blurb text. Update Everything on Login Restyling.docx Done: Completed and refined the Team Page and Login Styling requirements, including required team member fields, display/validation rules, styling-only login scope, authentication behaviour, redirect/access requirements, edge cases, and acceptance criteria. Deliverable: https://drive.google.com/file/d/1pL-fdZcbsttZaMG7yc4DqKOc-kywBS5R/view?usp=sharing Note for next role: Requirements have been reviewed and refined by the PM and are ready for UX review. Login work is styling-only and the existing authentication, validation, and session behaviour should not be changed.
UzNtmFGPkk6YbnjuW33_ScgAKfnS | [BOOTSTRAP RESTYLING] Design Login Style & Team Page Layout :120 | Done |  | Completed | Medium | Andi Jagila | Ngoc Chau Vu | 2026-08-07 | 2026-08-11 | 2026-08-10 |  | false | 2026-08-11 | Ngoc Chau Vu | 5/5 | Design shared with BA for validation;Login page mockup complete;Team page mockup complete;Document Updated;Visual consistency between the two checked | UX;Sprint 1 | Produce a mockup/wireframe of the restyled login page and a separate mockup of the team page layout, based on the BA's requirements document. Both must be visually consistent with each other. Update Task documentDocument.docx Done: Completed restyled mockups for login page and team page Deliverable: https://www.figma.com/design/28QcQyPENA1TtKSbWIYXBi/Untitled?node-id=0-1&t=BgdYufBNqm1oLQQB-1 Note for next role: Placeholders used instead of real member data, please swap in real content when available. Followed repo's docs/DESIGN.md for colors/fonts/spacing. Edge cases handled: Missing photo: initials fill the placeholder Long name: wraps, doesn't break the card Long blurb: line-clamp-3 + "Read more" Missing role/blurb: field collapses, card keeps shape Odd photo dimensions: object-cover, centre crop Login errors: validation + incorrect credential messages both stay visible on the form
vSEhbhF2pkeRfhpSOefj2MgANpre | [BOOTSTRAP RESTYLING]- Validate Design Against Requirements : 60 | Done |  | Completed | Medium | Shehryar Shaukat | Ngoc Chau Vu | 2026-08-07 | 2026-08-12 | 2026-08-10 |  | false | 2026-08-11 | Ngoc Chau Vu | 5/5 | Login scope confirmed unchanged;Design formally approved;Every required field checked against the design;Gaps (if any) sent back to UX and resolved;Document Updated | BA;Sprint 1 | Check the UX mockups against the requirements document. Confirm every field is represented, the login mockup stays styling-only, and edge cases have a visible design treatment. Flag any gaps back to UX before approving. Update Document.docx Done: Validated the final UX design against the approved BA requirements. All required fields were checked, the login scope was confirmed unchanged, any identified gaps were resolved with UX, and the final design was formally approved. Deliverable: https://www.figma.com/design/28QcQyPENA1TtKSbWIYXBi/Untitled?node-id=0-1&t=BgdYufBNqm1oLQQB-1 Note for next role: The final UX design has been validated against the approved requirements and is ready for development. Please implement the approved Sign In and Team Page designs while keeping the existing authentication logic, validation, and session behaviour unchanged.
PUyZYCApd0arOX8SdhNCVsgAHShu | [BOOTSTRAP RESTYLING]- Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only : 60 | Done |  | Completed | Medium | Manh Tuan Lam | Ngoc Chau Vu | 2026-08-07 | 2026-08-13 | 2026-08-10 |  | false | 2026-08-13 | Ngoc Chau Vu | 4/4 | Visual style matches approved mockup;Existing login validation/errors still function as before;No authentication logic changed;Update document | DEV;Sprint 1 | Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only. update Document.docx Done: restyled the existing login page to match the approved visual design, without changing authentication, validation, or session handling. Deliverable: https://github.com/tuanlam05/rmit-capstone Note for next role: styling-only changes. existing authentication logic, validation, and session handling were left unchanged. No known edge cases or out-of-scope changes
uQyHxI6ivUqV-qqwFH2HJsgANSfn | [BOOTSTRAP RESTYLING]- Build Team Page & Auth Redirect : 120 | Done |  | Completed | Medium | Manh Tuan Lam | Ngoc Chau Vu | 2026-08-07 | 2026-08-13 | 2026-08-10 |  | false | 2026-08-13 | Ngoc Chau Vu | 4/4 | Team page not directly accessible without login;Team page renders per design with all required fields;Document updated;Successful login redirects to team page | DEV;Sprint 1 | Build the team page per the approved design (name, member cards, blurb) and wire it so a successful login redirects the user here. The team page itself should not be reachable without a valid login. Update Doc Done: built the team page with the approved name, member cards, photos, roles, and blurbs; successful login now redirects to the team page, which is protected behind authentication. Deliverable: https://github.com/tuanlam05/rmit-capstone Note for next role: team page and auth redirect are implemented. Unauthenticated users are redirected away from the team page. Existing authentication and session handling were left unchanged.
ajHd_y4hlEaM4sZC6bWgGcgAI75T | [BOOTSTRAP RESTYLING] - Deploy - 120 | Done |  | Completed | Medium | Manh Tuan Lam | Ngoc Chau Vu | 2026-08-07 | 2026-08-13 | 2026-08-10 |  | false | 2026-08-13 | Ngoc Chau Vu | 4/4 | Document updated;Live URL loads without errors;Login → redirect → team page flow spot-checked on the deployed URL;Deployment completed via boilerplate pipeline | DEV;Sprint 1 | Deploy the updated application (restyled login + team page + redirect) using the boilerplate's deployment pipeline. Confirm the deployed version is live and functioning before handing off to Dev 2. Update Doc Done: deployed the restyled login, team page, and authentication redirect on Vercel, and verified the deployed version is live and functioning. Deliverable: https://rmit-capstone-frontend.vercel.app/ Note for next role: deployed version includes the approved login styling, team page, and post-login redirect. Verified that the deployment loads successfully and the authentication flow works as expected. Future commits on "main" branch will automatically update deployment.
o7RVY4WBGEm8Lyp_qnBNZcgAFl9s | [BOOTSTRAP RESTYLING] Test Login → Redirect → Team Page Flow : 60 | Done |  | Completed | Medium | Rishi Sood | Ngoc Chau Vu | 2026-08-07 | 2026-08-14 | 2026-08-10 |  | false | 2026-08-13 | Ngoc Chau Vu | 4/4 | All required content verified correct and complete;Document updated;Valid login tested end-to-end on deployed URL;Redirect to team page confirmed | DEV;Sprint 1 | On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Update Document Done: Completed manual testing on the login interface and Team Info page (deployed URL) including proper redirects, and verified all required content including member cards and UX elements to be complete. Deliverable: https://github.com/tuanlam05/rmit-capstone Note for next role: Login has been tested E2E, redirects function properly, member blurbs have some grammatical and punctuation errors. This has been fixed.
bJAZVsJuP0mmwZ5mThEle8gAAvRk | [BOOTSTRAP RESTYLING] - Test Edge Cases & Log Bugs : 60 | Done |  | Completed | Medium | Rishi Sood | Ngoc Chau Vu | 2026-08-07 | 2026-08-14 | 2026-08-10 |  | false | 2026-08-13 | Ngoc Chau Vu | 5/5 | Missing-photo and long-blurb edge cases tested;Bugs logged with repro steps, or none-found confirmed;Direct team-page access without login tested (must redirect);Update Document;Invalid login tested | DEV;Sprint 1 | Test edge cases identified by the BA: invalid login, direct team-page access without logging in, a missing photo, and an unusually long blurb. Log any bugs found back to Dev 1 with reproduction steps. Update Doc Done: Created unit tests for invalid logins and unauthorised team-page access redirect. Performed manual testing for missing-photo and long-blurb edge cases, and logged any bugs found in the Manual Testing Record. Deliverables: Manual Testing Record -https://drive.google.com/file/d/1QQ-090ffr2imqvjXb8Bza9iUQ1DyxL7P/view?usp=sharing Project Repo - https://github.com/tuanlam05/rmit-capstone Note for next role: The unit tests created for invalid login and redirect testing were successful. One bug was observed in manual testing where a long blurb will extend out of the member card when viewed in full. This has been fixed.
a26l81x2qUuraAl-j4rGBsgABMVO | [BOOTSTRAP RESTYLING] - Final Review & Sign-Off : 30 | Done |  | Completed | Medium | Ngoc Chau Vu | Ngoc Chau Vu | 2026-08-07 | 2026-08-15 | 2026-08-10 |  | false | 2026-08-14 | Ngoc Chau Vu | 3/3 | All prior tasks' checklists verified complete;Feature reviewed end-to-end against requirements and design;Task moved to Done | PM;Sprint 1 | PM reviews the completed feature end-to-end against the original requirements and design, confirms every prior task's checklist is complete, and signs off. Document is finalized ande signed off Done: Reviewed the completed feature end-to-end against the approved requirements and design, confirmed all prior tasks and checklists were completed, and provided final PM sign-off. Deliverable: https://planner.cloud.microsoft/webui/plan/oX5eDlBL4UKyl3dOH7jMucgAEudp/view/board?tid=d1323671-cdbe-4417-b4d4-bdb24b51316b Note for next role: None, the feature has been fully reviewed and approved, and the mock sprint is ready to be closed.

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
kMlAPPkaf0mSF-V2f1QjHMgAOziU | Labels | YobWUCoyQU-xUwdp7oUEXsgAEuNd |  | Not started | Medium |  | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 2026-08-07 |  |  |  | false
QbxsMkKnRkWu6R4_im8vWcgAG7N9 | [BOOTSTRAP RESTYLING] -Write requirements for team page + login styling : 60 | vdVCAAdli0KI7AszYocsqsgAJx7i |  | Completed | Important | fa197df4-b6ce-4fea-a734-172be904812e | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 2026-08-07 | 2026-08-10 | 2026-08-10 |  | false | 2026-08-11 | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 5/5 | Team page fields listed with validation/display rules;Edge cases documented;Login scope explicitly stated as styling-only;Document updated;Requirements shared with PM and UX | BA;Sprint 1 | Description Determine the content fields for the team page (name, photo, role, blurb) and confirm the login work is styling only, with no changes to existing auth logic or session behavior. Document edge cases such as missing photos or long blurb text. Update Everything on Login Restyling.docx Done: Completed and refined the Team Page and Login Styling requirements, including required team member fields, display/validation rules, styling-only login scope, authentication behaviour, redirect/access requirements, edge cases, and acceptance criteria. Deliverable: https://drive.google.com/file/d/1pL-fdZcbsttZaMG7yc4DqKOc-kywBS5R/view?usp=sharing Note for next role: Requirements have been reviewed and refined by the PM and are ready for UX review. Login work is styling-only and the existing authentication, validation, and session behaviour should not be changed.
UzNtmFGPkk6YbnjuW33_ScgAKfnS | [BOOTSTRAP RESTYLING] Design Login Style & Team Page Layout :120 | vdVCAAdli0KI7AszYocsqsgAJx7i |  | Completed | Medium | f5a062e7-4d47-42a4-a430-8001f18ecb7c | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 2026-08-07 | 2026-08-11 | 2026-08-10 |  | false | 2026-08-11 | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 5/5 | Design shared with BA for validation;Login page mockup complete;Team page mockup complete;Document Updated;Visual consistency between the two checked | UX;Sprint 1 | Produce a mockup/wireframe of the restyled login page and a separate mockup of the team page layout, based on the BA's requirements document. Both must be visually consistent with each other. Update Task documentDocument.docx Done: Completed restyled mockups for login page and team page Deliverable: https://www.figma.com/design/28QcQyPENA1TtKSbWIYXBi/Untitled?node-id=0-1&t=BgdYufBNqm1oLQQB-1 Note for next role: Placeholders used instead of real member data, please swap in real content when available. Followed repo's docs/DESIGN.md for colors/fonts/spacing. Edge cases handled: Missing photo: initials fill the placeholder Long name: wraps, doesn't break the card Long blurb: line-clamp-3 + "Read more" Missing role/blurb: field collapses, card keeps shape Odd photo dimensions: object-cover, centre crop Login errors: validation + incorrect credential messages both stay visible on the form
vSEhbhF2pkeRfhpSOefj2MgANpre | [BOOTSTRAP RESTYLING]- Validate Design Against Requirements : 60 | vdVCAAdli0KI7AszYocsqsgAJx7i |  | Completed | Medium | fa197df4-b6ce-4fea-a734-172be904812e | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 2026-08-07 | 2026-08-12 | 2026-08-10 |  | false | 2026-08-11 | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 5/5 | Login scope confirmed unchanged;Design formally approved;Every required field checked against the design;Gaps (if any) sent back to UX and resolved;Document Updated | BA;Sprint 1 | Check the UX mockups against the requirements document. Confirm every field is represented, the login mockup stays styling-only, and edge cases have a visible design treatment. Flag any gaps back to UX before approving. Update Document.docx Done: Validated the final UX design against the approved BA requirements. All required fields were checked, the login scope was confirmed unchanged, any identified gaps were resolved with UX, and the final design was formally approved. Deliverable: https://www.figma.com/design/28QcQyPENA1TtKSbWIYXBi/Untitled?node-id=0-1&t=BgdYufBNqm1oLQQB-1 Note for next role: The final UX design has been validated against the approved requirements and is ready for development. Please implement the approved Sign In and Team Page designs while keeping the existing authentication logic, validation, and session behaviour unchanged.
PUyZYCApd0arOX8SdhNCVsgAHShu | [BOOTSTRAP RESTYLING]- Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only : 60 | vdVCAAdli0KI7AszYocsqsgAJx7i |  | Completed | Medium | 7cafdee3-39bf-4961-b883-87883e1e7187 | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 2026-08-07 | 2026-08-13 | 2026-08-10 |  | false | 2026-08-13 | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 4/4 | Visual style matches approved mockup;Existing login validation/errors still function as before;No authentication logic changed;Update document | DEV;Sprint 1 | Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only. update Document.docx Done: restyled the existing login page to match the approved visual design, without changing authentication, validation, or session handling. Deliverable: https://github.com/tuanlam05/rmit-capstone Note for next role: styling-only changes. existing authentication logic, validation, and session handling were left unchanged. No known edge cases or out-of-scope changes
uQyHxI6ivUqV-qqwFH2HJsgANSfn | [BOOTSTRAP RESTYLING]- Build Team Page & Auth Redirect : 120 | vdVCAAdli0KI7AszYocsqsgAJx7i |  | Completed | Medium | 7cafdee3-39bf-4961-b883-87883e1e7187 | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 2026-08-07 | 2026-08-13 | 2026-08-10 |  | false | 2026-08-13 | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 4/4 | Team page not directly accessible without login;Team page renders per design with all required fields;Document updated;Successful login redirects to team page | DEV;Sprint 1 | Build the team page per the approved design (name, member cards, blurb) and wire it so a successful login redirects the user here. The team page itself should not be reachable without a valid login. Update Doc Done: built the team page with the approved name, member cards, photos, roles, and blurbs; successful login now redirects to the team page, which is protected behind authentication. Deliverable: https://github.com/tuanlam05/rmit-capstone Note for next role: team page and auth redirect are implemented. Unauthenticated users are redirected away from the team page. Existing authentication and session handling were left unchanged.
ajHd_y4hlEaM4sZC6bWgGcgAI75T | [BOOTSTRAP RESTYLING] - Deploy - 120 | vdVCAAdli0KI7AszYocsqsgAJx7i |  | Completed | Medium | 7cafdee3-39bf-4961-b883-87883e1e7187 | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 2026-08-07 | 2026-08-13 | 2026-08-10 |  | false | 2026-08-13 | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 4/4 | Document updated;Live URL loads without errors;Login → redirect → team page flow spot-checked on the deployed URL;Deployment completed via boilerplate pipeline | DEV;Sprint 1 | Deploy the updated application (restyled login + team page + redirect) using the boilerplate's deployment pipeline. Confirm the deployed version is live and functioning before handing off to Dev 2. Update Doc Done: deployed the restyled login, team page, and authentication redirect on Vercel, and verified the deployed version is live and functioning. Deliverable: https://rmit-capstone-frontend.vercel.app/ Note for next role: deployed version includes the approved login styling, team page, and post-login redirect. Verified that the deployment loads successfully and the authentication flow works as expected. Future commits on "main" branch will automatically update deployment.
o7RVY4WBGEm8Lyp_qnBNZcgAFl9s | [BOOTSTRAP RESTYLING] Test Login → Redirect → Team Page Flow : 60 | vdVCAAdli0KI7AszYocsqsgAJx7i |  | Completed | Medium | 106c9fcf-ad46-4221-9d00-6eb792a93997 | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 2026-08-07 | 2026-08-14 | 2026-08-10 |  | false | 2026-08-13 | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 4/4 | All required content verified correct and complete;Document updated;Valid login tested end-to-end on deployed URL;Redirect to team page confirmed | DEV;Sprint 1 | On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Update Document Done: Completed manual testing on the login interface and Team Info page (deployed URL) including proper redirects, and verified all required content including member cards and UX elements to be complete. Deliverable: https://github.com/tuanlam05/rmit-capstone Note for next role: Login has been tested E2E, redirects function properly, member blurbs have some grammatical and punctuation errors. This has been fixed.
bJAZVsJuP0mmwZ5mThEle8gAAvRk | [BOOTSTRAP RESTYLING] - Test Edge Cases & Log Bugs : 60 | vdVCAAdli0KI7AszYocsqsgAJx7i |  | Completed | Medium | 106c9fcf-ad46-4221-9d00-6eb792a93997 | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 2026-08-07 | 2026-08-14 | 2026-08-10 |  | false | 2026-08-13 | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 5/5 | Missing-photo and long-blurb edge cases tested;Bugs logged with repro steps, or none-found confirmed;Direct team-page access without login tested (must redirect);Update Document;Invalid login tested | DEV;Sprint 1 | Test edge cases identified by the BA: invalid login, direct team-page access without logging in, a missing photo, and an unusually long blurb. Log any bugs found back to Dev 1 with reproduction steps. Update Doc Done: Created unit tests for invalid logins and unauthorised team-page access redirect. Performed manual testing for missing-photo and long-blurb edge cases, and logged any bugs found in the Manual Testing Record. Deliverables: Manual Testing Record -https://drive.google.com/file/d/1QQ-090ffr2imqvjXb8Bza9iUQ1DyxL7P/view?usp=sharing Project Repo - https://github.com/tuanlam05/rmit-capstone Note for next role: The unit tests created for invalid login and redirect testing were successful. One bug was observed in manual testing where a long blurb will extend out of the member card when viewed in full. This has been fixed.
a26l81x2qUuraAl-j4rGBsgABMVO | [BOOTSTRAP RESTYLING] - Final Review & Sign-Off : 30 | vdVCAAdli0KI7AszYocsqsgAJx7i |  | Completed | Medium | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 2026-08-07 | 2026-08-15 | 2026-08-10 |  | false | 2026-08-14 | 26c4959f-ab38-4b0b-8782-5368a4343fbb | 3/3 | All prior tasks' checklists verified complete;Feature reviewed end-to-end against requirements and design;Task moved to Done | PM;Sprint 1 | PM reviews the completed feature end-to-end against the original requirements and design, confirms every prior task's checklist is complete, and signs off. Document is finalized ande signed off Done: Reviewed the completed feature end-to-end against the approved requirements and design, confirmed all prior tasks and checklists were completed, and provided final PM sign-off. Deliverable: https://planner.cloud.microsoft/webui/plan/oX5eDlBL4UKyl3dOH7jMucgAEudp/view/board?tid=d1323671-cdbe-4417-b4d4-bdb24b51316b Note for next role: None, the feature has been fully reviewed and approved, and the mock sprint is ready to be closed.

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
jkKyzGR_zkKPWUKHt9c4fcgABfaF | Blocked
YobWUCoyQU-xUwdp7oUEXsgAEuNd | Documents & Updates
TdaUU8lfSkGSEKHqkqFJdsgAEy5c | Backlog
vaOzIQ5eh0akBAiUcLWzAcgAB_zI | Doing
7Q97giIvNEy28S0P_nSV8sgAJD-Y | Reviewing
vdVCAAdli0KI7AszYocsqsgAJx7i | Done
0zY3Gnd6YUavL5Ylck0358gAKqPS | Testing
qMXCJz84j0qKaUs-GEEbz8gAFMjo | Done
49Slw6P1eUm2KuQBeLlPDMgAFQyw | Clean up

## Users
User ID | User Name | Email
26c4959f-ab38-4b0b-8782-5368a4343fbb | Ngoc Chau Vu | s4066600@rmit.edu.vn
fa197df4-b6ce-4fea-a734-172be904812e | Shehryar Shaukat | S3989752@student.rmit.edu.au
f5a062e7-4d47-42a4-a430-8001f18ecb7c | Andi Jagila | S4071278@student.rmit.edu.au
7cafdee3-39bf-4961-b883-87883e1e7187 | Manh Tuan Lam | S4037166@rmit.edu.vn
106c9fcf-ad46-4221-9d00-6eb792a93997 | Rishi Sood | s4004863@student.rmit.edu.au